## Sheet1
Risk | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures
Application goes offline | Application’s localhost: going down. This site can’t be reached | Low | High | Developer/ISP (Internet Service Provider) | Checking whether there is Internet connection; trying to restart the server | Make sure that you have Internet connection; make sure that the server is running before launching the application
Poorly written code | Can lead to a host of web application issues, such as inefficient algorithms, memory leak and application deadlocks | Medium | High | Developer | Checking the code | Making sure that you are using all the tools at your disposal, such as best programming practices like code reviews
Unoptimized database | It can destroy a production application. Missing indexes slow down the performance of SQL queries causing, which can drag down an entire site | Low | High | Developer | Checking the database | Making sure to use scripts and file statistics to check for any inefficient queries
Unexpected error codes | Sometimes, unexpected error codes arise and lack sufficient information of what exactly went wrong | High | Medium/High | Developer | Checking the code and trying to figure out what went wrong | Constantly running a piece of code, you have created and making sure it works, so when you create a new piece of code and an error occurs, you’d know that it is probably the code you have written now
Major changes in integrated development environments/ dependencies | Certain functions may not work anymore, or may need something additional | Medium | High | Developer | Research for updates regarding the new changes | Regular checking the changes and updates
Hardware chosen for the development project stops working | The project cannot be accessed as the hardware is malfunctioning | Low | High | Manufacturer | Bring the laptop to a technician who is able to fix it | Upload all your work in the cloud, or online repository such as GitHub, so you can retrieve your work if your machine dies
GitHub.com not working | Trying to commit/push changes but the repository is not responding or is down | Low | High | Git | Contacting Git staff members | Having a backup repository where you could upload your work, for example in the cloud
Hacked database | Data being lost and/or ransom | Medium | High | Secuity/Data Base Team | Contacting secutity/data base team | Regularly updating password associated with the credentials used to log in the database / Including special characters and symbols into the password
Losing work | Loss of work would resume the progress that has been advanced during the project, which would result in failure | Low | High | Developer | Panicking, trying to find if the work has been saved somewhere else, If not then starting from the beginning | Making sure to regualry save your work on the cloud, so in case of a distasted to be easily downloaded to your local device
Accident | Getting involved in an accident and not being able to continue work due to being hospitalised | Low | High | Not Applicable | Not Applicable | Not Applicable